## Slide 1
साथी
SAATHI
Minor Project · Phase 3
Planning, Budgeting, Task Definition & Preliminary Design
Smart City Citizen Services App
Saathi — one door to every government service. A multilingual, voice-first citizen app with an assistant that asks before it acts.
SUBMITTED BY
Krishom Sharma
BCA (UI/UX Designs)
UID — 24BCU10002
DEPARTMENT
UIC
University Institute of Computing
A design concept. Not affiliated with the Government of India.

## Slide 2: What this phase covers
Phase 3 plans the work, prices it, breaks it into tasks and shows the first design.
01
Methodology
Double Diamond, applied to a civic product
02
Project timeline
A 16-week plan with phase milestones
03
Work breakdown
Five workstreams, every task named
04
Task definition
Deliverable, duration and tools per task
05
Tools & resources
An open-source stack and test devices
06
Budget
Indicative costs — software at ₹0
07
Risks & mitigation
What could go wrong, and the plan
08
Information architecture
Five tabs with the assistant at the centre
09
Key flow — Saathi AI
Ask → plan → approve → done
10
Design system
Bharat Precision: colour, type, imagery, motion
11
Preliminary screens
Citizen app and department console

## Slide 3: Methodology — the Double Diamond
Diverge to understand, converge to define; diverge to explore, converge to deliver.
Problem space
Solution space
01 Discover
Field conversations · app audit · standards review
02 Define
Personas · problem statement · objectives · scope
03 Develop
IA · flows · design system · prototype · agent
04 Deliver
Testing · language review · build · case study

## Slide 4: Project timeline
Planned schedule across a 16-week semester, with the three phase reviews and the expo as milestones.
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
W16
Research & problem definition
Scope & literature review
Information architecture & flows
Design system (Bharat Precision)
Prototype screens & apply engine
Saathi AI — scripted agent
Department consoles
Website & case study
Testing & language review
Final build & submission
Phase 1 review
Phase 2 review
Phase 3 review
Project Expo
Define
Design
Build
Validate & ship

## Slide 5: Work breakdown structure
Five workstreams; every leaf is a task with an owner, an output and a date.
Saathi — Smart City App
1.0 Research
1.1
Citizen conversations
1.2
App & portal audit
1.3
Personas
1.4
Problem statement
2.0 Design
2.1
Information architecture
2.2
User flows
2.3
Design system
2.4
High-fidelity screens
3.0 Prototype
3.1
App shell & tabs
3.2
42 apply flows
3.3
Saathi AI agent
3.4
Dept. consoles
4.0 Language
4.1
Locale infrastructure
4.2
Hindi · Bengali · Tamil
4.3
13 machine-assisted
4.4
Per-script typography
5.0 Validation
5.1
Contrast tests
5.2
Agent unit tests
5.3
Usability sessions
5.4
Case study & expo

## Slide 6: Task definition
Each task, what it produces, how long it takes and what it is built with.
# | Task | Deliverable | Duration | Tools
T1 | User research & personas | 4 personas, frictions, quotes | 2 wks | Interviews, notes
T2 | Problem definition & scope | Problem statement, objectives, scope | 1 wk | Docs
T3 | Literature & benchmark review | Standards map, UMANG comparison | 2 wks | Web research
T4 | Information architecture | 5-tab IA, sitemap, user flows | 1 wk | Diagrams
T5 | Design system | Tokens, type, icons, imagery, motion | 2 wks | Tailwind, Phosphor
T6 | Prototype & apply engine | All screens + 42 apply flows | 4 wks | Next.js, React, TS
T7 | Saathi AI agent | 6 missions, consent gate, outcomes | 2 wks | TypeScript, Vitest
T8 | Department consoles | 15 consoles, audit trail | 2 wks | Next.js
T9 | Languages & accessibility | 17 locales, a11y modes, contrast tests | 2 wks | next-intl
T10 | Testing, website & submission | Case study, static build, expo deck | 2 wks | Hostinger

## Slide 7: Tools & resources
An open-source stack, so the software budget stays at zero.
Next.js 14 + React 18
App framework, static export
TypeScript
Typed models for flows and agent
Tailwind CSS
Design tokens as utility classes
Framer Motion
Springs, transitions, reduced motion
next-intl
23 locales, live language switch
Phosphor Icons
One icon family, three weights
Vitest
Unit tests for agent and contrast
Git & GitHub
Version control, one commit per phase
Hostinger
Static hosting for the live demo
Test devices
Android + iPhone, slow-network mode
Google Fonts / OFL
Geist, Instrument Serif, Anek, Noto
Chrome DevTools
Lighthouse, accessibility checks

## Slide 8: Budget — an indicative estimate
Student-project costs in ₹. Software, fonts and icons are open-source, so the spend goes on hosting and people.
Item | Cost (₹)
Web hosting (12 months) | 2,400
Usability testing — 8 participants | 2,000
Field research travel | 1,500
Mobile data & internet | 1,200
Domain name (1 year) | 800
Printing & report binding | 600
Software, fonts & icons | 0 · open source
Total (estimated) | ₹ 8,500
Chart: 
| Web hosting | Usability testing | Field research travel | Mobile data & internet | Domain name | Printing & report binding
Budget | 2400 | 2000 | 1500 | 1200 | 800 | 600
Indicative estimates for planning; actual prices vary by plan and provider.

## Slide 9: Risks & mitigation
What could derail the project, and what is already in place.
RISK
IMPACT
MITIGATION
Translations read as machine-made
High
Hindi, Bengali, Tamil authored by hand; 13 more flagged for native review before any pilot
Assistant acts without consent
High
Scripted, reviewable missions; consent gate in code; red-team the agent before release
Mistaken for an official app
Medium
Own brand mark, no emblem, disclaimer on every page, all data labelled sample
Scope creep across 42 flows
Medium
One shared apply engine; flows are data, not separate screens
Inaccessible to low-vision users
Medium
Contrast tested in code against WCAG 2.1 AA; larger text, read-aloud, slow mode
Slow on weak networks
Low
Static export, no 3D libraries, fonts load only for the script in use

## Slide 10: Information architecture
Five tabs. A bare “Apply” tab asks “apply for what?” — so the centre of Saathi is the assistant.
साथी Saathi
Home
Saathi ID card
Needs attention
My applications
Schemes for you
Explore
Life moments
Services (42 flows)
Schemes
Search, any language
Saathi AI
Ask by voice or text
Plan & sources
Consent gate
Outcome + receipt
Track
Applications
Status timeline
Named officers
“Why the delay?”
Me
Document wallet
Family / proxy
Privacy dashboard
Language & access

## Slide 11: Key flow — Saathi AI asks before it acts
Rakesh asks for his daughter's birth certificate, in Hindi. Four steps, one consent, real proof.
01
Ask
02
Plan
03
Approve
04
Done
मेरी बेटी का जन्म प्रमाणपत्र बनवाना है
“I need to get my daughter's birth certificate”
By voice or text, in any of 17 languages
Fetch the hospital birth record from DigiLocker
Fill Form 1 for e-District
Check Janani Suraksha Yojana eligibility
Submit to Nagar Nigam, Kanpur
Every step names its official source
Share with Nagar Nigam, Kanpur?
Your name and address
Aanya's hospital birth record
Valid until the application closes
Approve
Edit
Nothing leaves the phone without a yes
Application submitted
SAA-2026-457029
Priya Nair is reviewing it
Certificate expected in 7 days
You may also get ₹1,400 under Janani Suraksha Yojana.

## Slide 12: Design system — Bharat Precision
Calm enough to trust with a pension, precise enough to feel world-class.
COLOUR WITH A JOB
Chakra Navy
#1F43B8 · Actions, links, focus
India Green
#12803C · Verified, approved, done
Saffron
#FF8A1F · Highlights — never body text
Ink
#0B0D14 · Text
White
#FFFFFF · Every surface
TYPE ACROSS SCRIPTS
Aa
Precision.
साथी
நான் உதவலாம்
Geist for Latin UI · Instrument Serif for one emotive word · Anek (Ek Type, an Indian foundry) for Indic headlines · Noto Sans for Indic body at 1.8 line-height (UX4G) · Tiro Devanagari for the wordmark.
Kolam & guilloche
Imagery made in code — kolam line art and security linework. No stock photos, no maps.
Phosphor, one family
Regular for chrome, duotone for tiles, fill for the active tab.
Motion with a reason
UI motion under 300 ms, always interruptible; fades only for reduced motion.
Contrast, tested
Every text colour checked ≥ 4.5:1 against WCAG 2.1 AA in automated tests.

## Slide 13: Preliminary screens — citizen app
Onboarding with consent, a home that knows what needs attention, and services found by life moment.
Onboarding
Language first — 17 today
Home
Identity, nudges, applications
Explore
Life moments, services, schemes
A new baby
One checklist, many departments

## Slide 14: Preliminary screens — trust & status
The assistant, the timeline and the wallet — where trust is earned.
Saathi AI
Ask in any words
Track
Stages, officers and dates
Me
Tinted document wallet
Privacy & consent
Who used your data — revoke

## Slide 15: Both sides of the counter
The citizen's website and the officer's console — every decision reaches the citizen live, in their language.
Website — “One door to every government service”, with the live prototype embedded
Saathi for Departments — 15 consoles, masked e-KYC, audit trail

## Slide 16: Thank you.
Phase 3 planned the work, priced it, broke it into tasks and produced the first complete design of Saathi.
NEXT · BUILD, TEST & PROJECT EXPO
Usability sessions in three states, native-language review, and the live prototype at the expo.
Krishom Sharma · BCA (UI/UX Designs) · UID 24BCU10002